## Sheet1
SlNo | Feature | Story number | Description (Card) | Acceptance Criteria (Confirmation) | Initial Size Estimate (SP) | Business Priority | Sprint Number | Comments
1 | Customer Registration – JAVA Array | US00 | As a customer I should able to register myself | *In the console customer/admin should able to view themain menu as follows 1) Register 2)Login 3)Exit -On selecting 1, (customer/admin) should able to enter the customer id and password and login to the application if credentials are true. -On selecting 2, customer should able to enter the following details and register themself. 1)Customer name : A string with minimum 3 or maximum 50 character. 2) Email : A string which contains '@' . 3) Mobile number : A 10 digit number, 4)Password : A string which contains small letter, capital letter and atleast one alphabet. 5)Confirm password : A string which matches the password. 6) Address : A string with maximum 300 characters. *Once the registration is successful customer should able to view the message "registration successfull" along with the customer id (7 digit random number), email and mobile number. and they need to be redirected to main menu. -On selecting 3, customer/admin should able to end the application.
2 | Home page -JAVA Array | US00 | As a customer I should able to view the menu. | *In the console customer should able to view the following menu 1)View products 2)Payment 3)Previous orders 4)View profile 5)Logout -On selecting 1, customer should able to view the products available for purchase. -On selecting 2, customer should able to pay the purchase bill. -On selecting 3, customer should able to view the previous orders. -On selecting 4 .customer should able to view and edit the profile. -On selecting 5, customer should able to logout from the homepage and return to main menu.
3 | View Products-JAVA Array | US00 | As a customer I should able to view the available Products. | *In the console customer should able to view all the products available for purchase. -customer can able to select the product by entering there product id. -customer can able to select one product. -Amount need to be calculated for the selected product including taxes and it should be viewed by the customer before they proceed with the payment.
4 | Payment - JAVA Array | US00 | As a customer I should able to pay the purchase bill. | *In the console customer should able to view the payable amount and they should able to enter the card details to proceed with payment -Card No: A 16 digit number -Card Holder Name: A textbox with min 10 characters -Expiry Date <MM/YY> -CVV: A 3 digit number Once the payment is successful, they should be able to view the message as 'Payment successful' along with the order Id(12 digit randomly generated number) and amount paid.
5 | View Profile - JAVA Array | US00 | As a customer I should able to view the profile. | In the console Customer Sholuld able to view their profile as follows -Customer Id -Name -Email -Update password : with yes or no option By selecting (taking imput as) yes they should able to reset the password update.